## Risk Log
RiskID | Status | Description | Risk Owner | Created | Last Updated | Likelihood Score | Impact Score | Risk Score | Control / mitigation | Risk Treatment Option | Residual Likelihood Score | Residual Impact Score | Residual Risk Score | Update | Risk Treatment Plan Link For all risks of score >10
001 | Open | Information Security Governance: A lack of Information Security governance and overall policies, procedures, controls and oversight could lead to organisational lack of awareness and loss of data Confidentiality, Integrity and Availability. |  |  |  | 5 | 5 | 25 | [ORGANISATION] have established an Information Security framework based upon ISO 27001:2022. - Controls are grouped into 4 families; Organisational, People, Physical & Technology Controls. - As part of a continual cycle of improvement [ORGANISATION] will review risks and controls as per the Information Security policy. | Mitigate | 3 | 4 | 12
002 | Open | External cyber attack: Unpatched infrastructure, endpoints and applications leads to a successful ransomware attack compromising the confidentiality and availability of data, resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. |  |  |  | 5 | 4 | 20 | Google Workspace Admin and Security Centre controls configured for access management, 2FA, Strong Password. Anti Virus installed on endpoints. Web application firewall protection for web application. Security provided by Digital Ocean and AWS hosting. Vulnerability management and incident alerting in place. | Mitigate | 3 | 4 | 12
003 | Open | Social engineering: Colleagues are tricked into divulging sensitive data and / or access credentials, causing a breach of data confidentiality, resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. |  |  |  | 4 | 4 | 16 | Colleagues have induction training Web proxy restricts access to malicious website / adware. User access to data based on role so any loss should be contained. | Mitigate | 3 | 4 | 12
004 | Open | Distributed Denial of Service: The business suffers a Distribution Denial of Service (“DDoS”) attack causing significant loss of system availability, resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. |  |  |  | 4 | 4 | 16 | Perimeter monitoring of web traffic volumes / trends / patterns of what is considered normal, outsourced to Digital Ocean. Third party reviews and update meetings with vendors. | Mitigate | 3 | 3 | 9
005 | Open | Insider Threat: Data loss or leakage by colleagues due to malicious or erroneous / fraudulent activity, resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. |  |  |  | 3 | 4 | 12 | Staff training at induction. Data access restricted based on roles. Network segmentation restricts access to other areas. | Mitigate | 2 | 4 | 8
006 | Open | 3rd Party Supply Chain disruption: Malicious or erroneous / fraudulent activity is performed by a third-party supplier resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. Also includes loss of supplier services due to lack of resiliance or Disaster Recovery plan. |  |  |  | 2 | 5 | 10 | Supplier due diligence undertaken. Proactive engagement with suppliers. | Mitigate | 1 | 5 | 5
007 | Open | Non-compliance with legal and regulatory obligations: Data compromise, specifically relating to a confidentiality breach of customer and / or colleague personal data, resulting in a loss of market, heightened regulatory scrutiny / sanctions and poor reputational damage. |  |  |  | 4 | 3 | 12 | Recent external independent information security control gap assessment has been completed as part of our continual improvement strategy. Action plan has been formed to enhance controls. | Mitigate | 2 | 3 | 6
008 | Open | Weak Authentication: Risks associated with weak passwords or lack of multi-factor authentication. |  |  |  | 4 | 4 | 16 | Strong Password Policies: Implement policies that require complex passwords (a mix of letters, numbers, and special characters) and regular password changes. Multi-Factor Authentication (MFA): Introduce MFA wherever possible. This requires users to provide two or more verification factors to gain access, significantly enhancing security. Password Management Tools: Encourage the use of password managers to help users maintain strong, unique passwords for different services without the risk of forgetting them. Regular User Education: Conduct regular training sessions to educate users about the importance of strong authentication practices. Biometric Authentication: Where feasible, implement biometric authentication methods like fingerprint or facial recognition for added security. Regular Audits and Monitoring: Conduct regular audits of authentication methods and monitor for any unusual login attempts or failures. | Mitigate | 2 | 4 | 8
009 | Open | Mobile Device Vulnerabilities: Security risks related to the use of mobile devices in corporate networks. |  | 2023-01-23 | 2023-11-23 | 3 | 4 | 12 | Mobile Device Management (MDM) Software: Implement MDM solutions to control and secure the mobile devices that access corporate networks. Use of VPNs: Require the use of Virtual Private Networks (VPNs) for accessing corporate resources from mobile devices. Regular Software Updates: Ensure that all mobile devices are regularly updated with the latest security patches. Device Encryption: Enforce encryption of data stored on mobile devices. Remote Wipe Capabilities: Implement remote wipe capabilities to erase data on lost or stolen devices. Secure Wi-Fi Practices: Educate users about the risks of public Wi-Fi and provide guidelines for secure mobile working. | Mitigate | 2 | 3 | 6

## Impact & Probability Scoring
IMPACT | Catastrophic | 5 | 5 | 10 | 15 | 20 | 25
| Major Disruption | 4 | 4 | 8 | 12 | 16 | 20
| Moderate / Workaround | 3 | 3 | 6 | 9 | 12 | 15
| Minor / Inconvenience | 2 | 2 | 4 | 6 | 8 | 10
| Insignificant | 1 | 1 | 2 | 3 | 4 | 5
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Remote | Unlikely | Possible | Probable | Highly Probable
LIKELIHOOD